## Slide 1: Progress on the Real-World Data Pipeline (Phase 0908)
Weekly Lab Meeting
2026
1 Graduate School of Information Science and Technology, Osaka University
2 RIKEN Center for Computational Science
(Enter presenter name)
September 8, 2026

## Slide 2: Recap of the Last Meeting (Aug 17)
Simulation work (the grid-mismatch question) is on hold for now
Main focus: collect real-world training data, and build post-processing to see actual results
A new open question emerged: how to feed angle information into the model — decision deferred to today (9/8)
  Collapse angle via DBF into a RAD tensor, or feed the raw complex phase directly
  DBF quantizes to 14.5° (≈ ±10 m at 40 m range) — two orders of magnitude coarser than the 0.13 m label precision

## Slide 3: Goal and Structure of Phase 0908
Goal: gather the evidence (real SNR, inter-element phase stability) needed to decide DBF vs. raw phase
In parallel, collect real-world training data that will be usable either way
Pipeline: simultaneous radar+camera capture → radar: complex RD extraction / camera: YOLO+ByteTrack detection → association → ground-plane (X, Y) labeling
Post-processing (CFAR + NMS + tracking) and the raw-phase model prototype are model-agnostic pieces that can proceed in parallel
All the desk-work components (sync, association skeleton, post-processing, camera calibration, .dat header decoding) are done — the bottleneck is now the actual field shoot

## Slide 4: Progress This Week
H8: Located the Remove-Static-Clutter flag in the .dat header (0x72, 1 byte)
S1: Verified radar–camera time sync (camera frame count matches radar frame count, 50=50, over two 10-second runs)
S3: Implemented the camera–radar association skeleton and validated it on synthetic data (calibration on real data is still pending)
S5: Implemented post-processing (peak extraction → NMS → tracking) and confirmed SNR-dependent detection rate and track continuity on synthetic data
H3/S2: Completed intrinsic camera calibration (3840×2160, RMS 1.35 px); the estimated height/tilt angle still needs validation
Resolved duplicate bicycle/motorcycle detections inside merge_cyclist()

## Slide 5: Open Issues
Most open items — including the core DBF-vs-raw-phase question — are blocked on real measurement data
Risk that class discrimination collapses into a speed threshold: existing recordings already separate pedestrian vs. cyclist cleanly by Doppler alone
  Mitigation: include runs where the cyclist rides at walking speed in the shooting plan
Manual, location-dependent marker selection is a likely bottleneck — considering a switch to ArUco/ChArUco markers
Handling of track_id = -1 remains deferred, prioritizing the risk of mismatched associations

## Slide 6: Next Steps
H1: Two field shooting sessions (weekend, in the lab) — radar and camera running simultaneously
  Scenarios: solo baselines, walking-speed cyclist, close cyclist+pedestrian, two close cyclists, crossing paths — 7 categories × 20 runs each
Remaining items from the advisor's 6 points: window open/closed comparison, Remove-Static-Clutter ON/OFF comparison, reflector-based range-axis check — all within the same session
Once real data is in hand: calibrate S3's association gates, validate 3+-target association, assemble the S4 supervision tensor, and decide DBF vs. raw phase
Cross-check the measured height/tilt angle against the checkerboard-calibration estimate